## Sheet1
[7 empty] | Year: | 2024-01-08 |  |  |  |  | 2024-02-12 |  |  |  | 2024-03-11 |  |  |  | 2024-04-08 |  |  |  |  | 2024-05-13
| Project Start Date: | 2024-01-28 |  |  |  |  | Month: | 2024-01-08 |  |  |  |  | 2024-02-12 |  |  |  | 2024-03-11 |  |  |  | 2024-04-08 |  |  |  |  | 2024-05-13
| Project Name: | Product Data Management of Engine Oil Drainer Using Teamcenter |  |  |  |  | Week Starting: | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-29 | 2024-05-06 | 2024-05-13
S.NO | ACTIVITY | ASSIGNED TO | START | END | DAYS | STATUS | % DONE
1 | Project Title Confirmation | Jesmond franc R | 2024-01-28 | 2024-01-30 | 2 | Completed | 100% | bar: 2024-01-29
2 | Fact-Finding the Project | Navaneethan S | 2024-01-31 | 2024-02-06 | 5 | Completed | 100% | bar: 2024-02-05
3 | Delving the Components of the Machine | Jesmond franc R | 2024-02-07 | 2024-02-09 | 3 | Completed | 100% | bar: 2024-02-05
4 | Detailed Design | Navaneethan S | 2024-02-10 | 2024-02-24 | 10 | Completed | 100% | bar: 2024-02-19
5 | Analysis of Designed Product | Navaneethan S | 2024-02-25 | 2024-03-03 | 5 | Completed | 100% | bar: 2024-02-26
6 | Integrating with Teamcenter Modules | Jesmond franc R & Navaneethan | 2024-03-04 | 2024-03-18 | 11 | Completed | 100% | bar: 2024-03-18
7 | Manufacturing of the Product | Jesmond franc R | 2024-03-19 | 2024-03-31 | 9 | Completed | 100% | bar: 2024-03-25
8 | Testing and Validation | Jesmond franc R & Navaneethan | 2024-04-01 | 2024-04-02 | 2 | Completed | 100% | bar: 2024-04-01
9 | Report Generation | Jesmond franc R & Navaneethan | 2024-04-03 | 2024-04-20 | 13 | Completed | 100% | bar: 2024-04-15
10 | Conference | Jesmond franc R & Navaneethan | 2024-04-17 | 2024-04-17 | 1 | Completed | 100%
11 | Final Presentation | Jesmond franc R & Navaneethan | 2024-04-25 | 2024-04-25 | 1 | Completed | 100%
Formulas:
DAYS = IF([END]="","",NETWORKDAYS([START],[END]))
END = [START]+2